| Coastal Erosion from Space |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Coastal Erosion Phase 2 Project Management Plan Ref: SO-RP-ARG-003-055-012 Date: 21/05/2020 |  |  |  |  |  |
| Customer: ESA Contract Ref.: 4000126603/19/I-LG |  |  |  |  |  |

This page is intentionally left blank

# Signatures

|  | Name | Company or Institute | Date |
| --- | --- | --- | --- |
| Prepared by | Martin Jones | ARGANS | 06/02/2020 |
| Authorised by | Craig Jacobs | ARGANS | 06/02/2020 |

# General Information

| Project Name: | Coastal Change Project Management Plan |
| --- | --- |
| Client: | ESA |
| Prime Contractor: | ARGANS |
| ARGANS Project Lead: | Martin Jones |
| Project Team: | - ARGANS -PM – VNIR Service Gp - IsardSAT – SAR Service Gp - AdwaisEO – Data Service Gp - British Geological Society – User Gp - Geological Survey Ireland - User Gp - IH Cantabria – User Gp - ARCTUS – User Gp - IGN FI |
| Start Date: (Phase 2) | 3rd April 2019 (Phase 1 start = TO 0) |
| Official End Date: | - Phase 1 3 January 2020 (MTR 24 Jan 2020) - Phase 2 3 April 2021 (FR 18-22 Jan 2021) |
| Current Estimated End Date: | - Phase 2 30 Mar 2021 |

# ARGANS Project Team

| Role | Name | Affiliation | Work package lead | % fte |
| --- | --- | --- | --- | --- |
| Project Manager | Martin Jones (MCJ) | ARGANS UK | Project Management | 50% |
| Technical Lead (EO) | Anne-Laure Beck (ALB) | ARGANS UK | EO lead | 75% |
| Technical Lead (Geomorphology) | Noelia A Zorrilla (NZ) | ARGANS UK | Geomorphology lead | 100% |
| Technical Lead (Software Dev) | Dr Stephen Emsley | ARGANS UK | Data and Delivery | 50% |
| EO Scientist | Martina Polito (MP) | ARGANS UK | SDB | 100% |
| EO Scientist | Eszter Magyar (EM) | ARGANS UK | VNIR Waterlines and Pre-Processing | 100% |
| EO Scientist | Amine Taji (AT) | ARGANS Mor | Geolocation | 50% |
| EO Scientist | Scott Miles (SM) | ARGANS UK | Shorelines | 100% |
| EO Scientist | Gilbert Langois (GL) | ARGANS Fr | Erosion Rate | 50% |

# Client Information

| Name | Role | e-mail |
| --- | --- | --- |
| Olivier Arino | ESA Technical Officer | Olivier.arino@esa.int |
| Fabrizio Ramoino | ESA Dep Tech Officer | Fabrizio.Ramoino@esa.int |

# Partners Information (User Group)

| Organization | Name | Role | e-mail |
| --- | --- | --- | --- |
| BGS | Andres Payo | Lead contact and User Team Lead | a.garcia@bgs.ac.uk |
| GSI | Xavier Monteys | Lead contact | Xavier.Monteys@gsi.ie |
| IHC | Jara Martinez Sanchez | Lead contact | Jara.martinez@unican.es |
| Arctus | Thomas Jaegler | Lead contact | tj@arctus.ca |
| IsardSAT | Albert Garcia-Mondejar | Lead Contact | albert.garcia@isardsat.cat |
| IGN FI | Benoit Kiene | Lead Contact | bkiene@ignfi.fr |

# Partners Information (Service Group)

| Organization | Name | Role | e-mail |
| --- | --- | --- | --- |
| IsardSAT | Albert Garcia-Mondejar | SAR Lead | albert.garcia@isardsat.cat |
| AdwaisEO | Giovanni Corato | Data storage and processing lead | giovanni.corato@adwaiseo.eu |

# Project Information

| Funder | ESA Science for Society Element of Earth Observation Envelope Program (EOEP-5, block 4) |  |
| --- | --- | --- |
| Value | Fixed Price for Phases 1 and 2 - Phase 1 – Euro 500,000 - Phase 2 – Euro 1,000,000 |  |
| Summary | Project Summary: - To develop and demonstrate innovative use of EO Products to be used by “user communities” responsible for monitoring and controlling coastal erosion. - Analysis of over 1,000 kms of coastline across four member states. - Extraction of shoreline and erosion trends over 25 years of ESA archive data. |  |
| List of deliverables | Phase 1 | MS#1 (50% Phase 1 payment): (KO+4) - Requirement Baseline Document (RB), |
|  |  | MS#2 (50% Phase 1 payment): (KO+9) - Mid-term Report (MTR) - Technical Specifications (TS) - Product Validation Plan (PVP) - Product Delivery (Prod) |
|  | Phase 2 | MS#1 (30% Phase 2 payment): (KO+13) - Validation product delivery (Prod) |
|  |  | MS#2 (50% Phase 2 payment): (KO+18) - Product Delivery 1st series of AOI (Prod) |
|  |  | MS#3 (20% Phase 2 payment): (KO+24) - Product Validation Report (PVR) - Final Report (FR) - Final Product Delivery (Prod) - Contract Closure Document (CCD) |

# Risks

| Issue/Risk: | Description: | Mitigation: |
| --- | --- | --- |
| Risk: Access to Auxiliary data |  |  |
| Risk: Access to TPM |  |  |
| Risk: 3D volume and erosion rate calculations |  |  |
| Risk: Product/Service Dissemination |  |  |
| Risk: Appropriate validation |  |  |
| Issue: Data/product naming & metadata protocol |  |  |

# Project Plan

| Milestone | Deliverable | Deliverable description | Delivery (Planned) | Delivery (predicted) |
| --- | --- | --- | --- | --- |
|  | Phase 2 Planning | Internal 2-6 February 2020 Service Providers 10 February 2020 Full consortium 12 February 2020 |  |  |
|  | Test Site processing | All Landsat 5/8 and Sentinel 2 Images downloaded. TPM received Geolocation conducted, images correctly named and stored in AdwaisEO Waterlines manufactured/named correctly and stored at AdwaisEO | 13 Mar 20 13 Mar 20 20 Mar 20 27 Mar 20 |  |
|  |  | Shorelines, Coastal Strip Feature Maps, SDB DTMs all manufactured | 3 Apr 20 |  |
|  | Test Site Delivered | Delivering WLs, SLs, Feature Maps, SDBs for all 6 test sites (El Prat, Tordera, StartBay, Wexford, Longue-Pointe de Mingan) for 25 years | 3 Apr 20 | Complete |
|  | Service Group Webservice Mtg | Data naming, file structure, metadata and data base design agreed | 11 Mar 20 | Delivered |
|  | Progress Meeting | Consortium Mtg and Progress Report # 6 | 19 Mar 20 | Delivered |
|  | Progress Report #6 | Progress Report #6 (February and March 2020) Ref: SO-RP-ARG-003-055-012 Date: 01/04/2020 | 1 Apr 20 | DELIVERED |
|  | Web service development Part 1 | Initial webservice testing complete: Access to the phase 1 site data is via the GeoPortal on the Coastalerosion.argans.co.uk website | 3 Apr 20 | Delivered |
|  | PRODUCTION |  |  |  |
|  | Phase 2 Ireland (part 1) | 4 week cycle download Landsat 5&8/Sentinel 2 (L1 -Sen2Cor to L2) & L2, geolocate, derive WLs, SLs, SDB, Coastal Strip Maps | April 20 | Delivered |
|  | Evaluation Report (ER v1.0) | User Evaluation Reports that shall be attached to the Product Validation Report. | 24 Apr 20 | Delivered |
|  | Product Validation Review (PVR v1.0) | The results of the product validation shall be documented in the Product Validation Report (Deliverable 2.2) | 1 May 20 | DELIVERED |
| MS#3 | Validation Products | Upon delivery and acceptance by the Agency of the 1st series of validation products | 1 May 20 | DELIVERED |
|  | Service Group Webservice Mtg | Data naming, file structure, metadata and data base design implemented | 13 May 20 | Delivered |
|  | ENGAGE | Maxar Conference | 19-20 May 20 | postponed |
|  | GEO Business | London Conference | 24-25 Sep 20 | postponed |
|  | Progress Meeting | Consortium Mtg and Progress Report # 7 | 27 May 20 |  |
|  | VALIDATION & ANALYSIS |  |  |  |
|  | Phase 2 Ireland (part 1 V&A) | 4 week cycle to validate and conduct initial analysis. | May 20 |  |
|  | Phase 2 Canada (part 1) | 4 week cycle download Landsat 5&8/Sentinel 2 (L1 -Sen2Cor to L2) & L2, geolocate, derive WLs, SLs, SDB, Coastal Strip Maps | May 20 | In Progress |
|  | Phase 2 Canada (part 1 V&A) | 4 week cycle to validate and conduct initial analysis. | Jun 20 |  |
|  | Phase 2 Spain (part 1) | 4 week cycle download Landsat 5&8/Sentinel 2 (L1 -Sen2Cor to L2) & L2, geolocate, derive WLs, SLs, SDB, Coastal Strip Maps | Jun 20 |  |
|  | 8th Symposium | Livorno Conference | 19-21 Jun 20 | postponed |
|  | Service Group Webservice Mtg | User Group updates and amendments to the webservice agreed | 10 Jul 20 |  |
|  | Phase 2 Spain (part 1 V&A) | 4 week cycle to validate and conduct initial analysis. | Jul 20 |  |
|  | Phase 2 England (part 1) | 4 week cycle download Landsat 5&8/Sentinel 2 (L1 -Sen2Cor to L2) & L2, geolocate, derive WLs, SLs, SDB, Coastal Strip Maps | Jul 20 |  |
|  | Phase 2 England (part 1 V&A) | 4 week cycle to validate and conduct initial analysis. | Aug 20 |  |
|  | Phase 2 Ireland (part 2) | 4 week cycle download Landsat 5&8/Sentinel 2 (L1 -Sen2Cor to L2) & L2, geolocate, derive WLs, SLs, SDB, Coastal Strip Maps | Aug 20 |  |
|  | Web service development Part 2 | Access (including User group amendments) to the all data is via the GeoPortal on the Coastalerosion.argans.co.uk website | 12 Aug 20 |  |
|  | Progress Meeting | Consortium Mtg and Progress Report # 8 | 10 Sep 20 |  |
|  | WORKSHOP 1 | Location tbc | Date tbc |  |
|  | GEO Business | London Conference | 24-25 Sep 20 | New Date |
|  | Phase 2 Ireland (part 2 V&A) | 4 week cycle to validate and conduct initial analysis. | Sep 20 |  |
|  | Phase 2 Canada (part 2) | 4 week cycle download Landsat 5&8/Sentinel 2 (L1 -Sen2Cor to L2) & L2, geolocate, derive WLs, SLs, SDB, Coastal Strip Maps | Sept 20 |  |
|  | Phase 2 Canada (part 2 V&A) | 4 week cycle to validate and conduct initial analysis. | Oct 20 |  |
|  | Product Validation Review (V 2) | The results of the product validation shall be documented in the Product Validation Report (Deliverable 2.2) | 3 Oct 20 |  |
|  | FINAL REPORT (Draft v1.0) | The Contractor shall summarise, in a final report (Deliverable 2.3), all findings of the project from the requirements collection up to the service roll-out analysis. | 3 Oct 20 |  |
| MS#4 | Product Delivery | Upon delivery and acceptance by the Agency of 1st products for AOIs | 3 Oct 20 |  |
|  | ICE Conference |  | Oct dtbc |  |
|  | WORKSHOP 2 | Location tbc | Date tbc |  |
|  | Phase 2 England (part 2) | 4 week cycle download Landsat 5&8/Sentinel 2 (L1 -Sen2Cor to L2) & L2, geolocate, derive WLs, SLs, SDB, Coastal Strip Maps | Oct 20 |  |
|  | Phase 2 England (part 2 V&A) | 4 week cycle to validate and conduct initial analysis. | Nov 20 |  |
|  | Phase 2 Spain (part 2) | 4 week cycle download Landsat 5&8/Sentinel 2 (L1 -Sen2Cor to L2) & L2, geolocate, derive WLs, SLs, SDB, Coastal Strip Maps | Nov 20 |  |
|  | PILOT DEMONSTRATION SERVICE | Coastalerosion.argans.co.uk GOES LIVE - FULL DEMO The service demonstration shall include the generation of all service products (Deliverable 2.1) specified in the Technical Specifications | 5 Nov 20 |  |
|  | WORKSHOP 3 | Location tbc | Date tbc |  |
|  | Phase 2 Spain (part 2 V&A) | 4 week cycle to validate and conduct initial analysis. | Dec 20 |  |
|  | WORKSHOP 4 | Location tbc | Date tbc |  |
|  | FINAL REPORT (Final v2.0 Privileged) | The Contractor shall summarise, in a final report (Deliverable 2.3), all findings of the project from the requirements collection up to the service roll-out analysis. This privileged version, with company-related particulars is for ESA internal use. | 14 Dec 20 |  |
|  | FINAL REPORT (Final v2.0 Public) | A public version for public dissemination for publication on SSEP web site. | 14 Dec 20 |  |
|  | Progress Meeting | Consortium Mtg and Progress Report # 9 (FR Planning) | 9 Dec 20 |  |
|  | Final Review | Frascati 2 day conference | 18-22 Jan 21 |  |
|  | Contract Closure Doc |  |  |  |
| MS#5 | FINAL REVIEW CONFERENCE |  | 3 Feb 21 |  |

# Conclusion

This Project Management Plan is a live document and it will be used to track progress and to ensure that all requirements of the Statement of Work and the Contract are delivered.